## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0003-D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0623 |  |  | Transmital Date: 22/Feb/2022
Document Title: PMR For Pressure Vessels |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0104-ME-TR-0623 |  |  | Transmital Date: 22/Feb/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0003-D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بازگشت به نامه ی شماره BK-PEDCO-NISOC-0011-ME-LT-2519 (سیستمی 26381 مورخ 1400/11/30)، به اطلاع می رساند مدارک MR پس از تولید و نهایی شدن کلیه مدارک مهندسی تفضیلی مربوطه (مانند مشخصات فنی، داده برگ ها، PMS و MTO ...) می بایست تولید گردد، چرا که تمامی مدارک مذکور در مورد هر پکیج خرید، می بایست با درج ویرایش نهایی و عنوان آن در متن، ضمیمه MR ها شوند. از آنجایی که مدارک مهندسی مرتبط تا کنون نهایی نشده اند، لذا تولید این مدارک در این مقطع مورد تایید نبوده و قابل بررسی نیز نمی باشد. |  | 00/2294/438942 | 1400/12/16 | باتوجه به انتشار کلیه مدارک و پیوست های مورد نیاز مدرک مذکور و همچنین برگزاری جلسات HAZOP & HAZID و نهایی شدن وضعیت مدارک پروژه، لذا خواهشمند است جهت تسریع در امور خرید، بررسی مدرک در دستور کار کارفرمای محترم قرار گیرد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Azizian | Signature | H.naserizadeh |  |  | Clarified By: H.Adineh | Signature
| Date:1400/12/16 |  |  |  |  | Date: 09/14/2022