## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0002_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0512 |  |  | Transmital Date: 26/Jan/2022
Document Title: PMR for GAS DEHYDRATION PACKAGE |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0011-ME-TR-0512 |  |  | Transmital Date:26/Jan/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدرک MR پس از تولید ونهایی شدن کلیه مدارک مهندسی تفضیلی مربوطه (مانندمشخصات فنی، داده برگ ها، PMS, MTO می بایست تولید گردد، چرا که تمامی مدارک مذکور در مورد هر پکیج خرید، می بایست با درج ویرایش نهایی و عنوان آن در متن، ضمیمه MR ها شوند.از آنجا که مدارک مهندسی مرتبط تاکنون نهایی نشده است، لذا تولید این مدرک در این مقطع مور تایید نبوده است. |  | 00/2294/445084 | 1400/12/21 | باتوجه به انتشار کلیه مدارک و پیوست های مورد نیاز مدرک مذکور و همچنین برگزاری جلسات HAZOP & HAZID و نهایی شدن وضعیت مدارک پروژه، لذا خواهشمند است جهت تسریع در امور خرید، بررسی مدرک در دستور کار آن کارفرمای محترم قرار گیرد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: H.Ghadyani | Signature | M.Fakharian
| Date: |  |  |  |  | Date:09/18/2022