## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-PR-LI-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0628 |  |  | Transmital Date: 23.Feb.2022
Document Title: Consumption List |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0628 |  |  | Transmital Date: 23.Feb.2022
[5 empty] | CRS No: NISOC-CRS-BK-SSGRL-PEDCO-110-PR-LI-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | میزان 250 لیتر درروز به عنوان سرانه مصرف آب زیاد درنظر گرفته شده است ، این میزان سرانه مصرف در شبانه روز برای فعالیت قابل انتظار دراین مجموعه قابل قبول نبوده و حتی دو برابر میانگین سرانه جهانی مصرف برای هرفرد خانوار شهری است. |  | 00/2294/445285 | 1400/12/21 | با توجه به توافقات حاصله شفاهی میزان مصرف روزانه به عدد 100 لیتر در هرروز کاهش یافت و محاسبات بازبینی گردید.
2 | پیشنهاد سازنده درخصوص میزان مصرف گازوییل مورد نیاز به عنوان اسنادمثبته ارائه گردد. |  | 00/2294/445285 | 1400/12/21 | کاتالوگ مشابه ظرفیت مورد نیاز به عنوان پیوست اضافه گردید ، همچنین براساس چارت های موجود و استاندارد ، محاسبات دیزل مورد نیاز در متن مدرک اضافه گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021