## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-PL-DW-0013 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-TR-1184 |  |  | Transmital Date:7/23/2022
Document Title: Pipeline Standard Drawing For Cover Slabs And Set-On-Weight |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0013-PL-TR-1184 |  |  | Transmital Date:7/23/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-PL-DW-0013_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به تغییرات کلی مدرک ضروری است دلایل بروز این تغییرات مشخص گردد. |  | 1401-2294-175032 | 1401/05/22 | مدرک مطابق با نقشه های استاندارد بروز رسانی شد
2 | موارد مندرج در بند 2، 3 و 4 برگ پاسخ (REPLY SHEET) رفع نشده است. ضروری است ضمن اصلاح مدرک، موارد با ابرک در مدرک نشان داده شود. |  | 1401-2294-175032 | 1401/05/22 | همگی موارد اعمال شدند.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: