## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-TE-PY-0005 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1118 |  |  | Transmital Date: Jun-26th-2022
Document Title: Telecom Equipment Layout For Area |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-TE-TR-1118 |  |  | Transmital Date: Jun-26th-2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-NISOC-120-TE-PY-0005_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اینکه تجهیز PABX در این پروژه موضوعیت ندارد ،در بخش هایی از مدارک عبارت PABX درج گردیده که می بایست با TELECOM EQUIPMENT جایگزین گردد |  | 1401-2294-124365 | 1401-04-10 | جایگزینی عبارات PABX با Telecom Equipment اعمل گردید.
2 | بر اساس مدرک پایه قطر رشته کابلهای مخابراتی OUTDOOR می بایست 0.8 در نظر گرفته شود. مقتضی است مدرک بر این اساس اصلاح گردد |  | 1401-2294-124365 | 1401-04-10 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: AP.Golrang | Signature |  |  |  | Clarified By: | Signature
| Date: Jul-05th-2022 |  |  |  |  | Date: