## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-TE-PY-0005 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1118 |  |  | Transmital Date: Jun-26th-2022
Document Title: Telecom Equipment Layout For Area |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-TE-TR-1118 |  |  | Transmital Date: Jun-26th-2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-TE-PY-0005_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بازگشت به مدارك مطالعات مهندسي پايه – پيوست 18 پيمان في مابين - در خصوص بلاك دياگرام سيستم هاي Telephone & Paging & Radio كه در فايل پيوست به شماره مدرك 1560-BK-NCS-TL-DIA-0001-04 قابل مشاهده است، تعداد اقلام مخابراتي در زيرسيستم هاي مورد اشاره در ترانسميتال TR-1118 با حداقل هاي بيان شده در مدرك مهندسي پايه متناسب نيست. علي ايحال باتوجه به تاييد مدرك BK-GCS-PEDCO-120-TE-BD-0004_D03 (Block Diagram For PABX) توسط ذينفع اصلي پروژه، تعداد اقلام مخابراتي در محوطه سايت - process area - در مدرك Telecom Equipment Layout For Area متفاوت از تعداد تلفن هاي Outdoor تاييد شده در مدرك Block Diagram ميباشد. از اين رو ضروريست تا پيمانكار دلايل فني و كارشناسي خودر را در خصوص كاهش تعداد اقلام مخابراتي مورد نياز ذينفع اصلي پروژه بيان نمايد. |  | BK-SUR-ENG-TEL-01-04994 | Jul-05th-2022 | مدرک بلوک دیاگرام شماتیک کلی از اتصال می باشد و تعداد تجهیزات در مدارک جانمایی طرح دیتیل نهایی گردید . لذا نسخه نهایی مدارک بلوک دیاگرام بر اساس آخرین ویرایش نقشه های جانمایی تایید شده ارسال میگردد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: AP.Golrang | Signature |  |  |  | Clarified By: | Signature
| Date: Jul-05th-2022 |  |  |  |  | Date: