## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-TE-MT-0003_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1004 |  |  | Transmital Date:MAY-25th-2022
Document Title: MTO FOR TELECOM EQUIPMENT |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-TE-TR-1004 |  |  | Transmital Date:MAY-25th-2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-TE-MT-0003_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بر اساس نامه شماره 4294 با توجه به اینکه تجهیز PABX در این پروژه موضوعیت ندارد، نام مدرک با عنوان PABX به Telecom Equipment تغییر یابد. لذا نام این مدرک به MTO for Telecom Equipment تغییر یابد. |  | 1401-2294-100876 | 1401-03-23 | اعمال گردید
2 | یک دستگاه تلفن ضد انفجار می بایست به چیدمان تلفن های محوطه اضافه گردد- مدرک MTO بر این اساس اصلاح گردد. |  | 1401-2294-100876 | 1401-03-23 | اصلاح گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: AP.Golrang | Signature |  |  |  | Clarified By: | Signature
| Date: 06-08th-2022 |  |  |  |  | Date: