## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-TE-MT-0004_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1004 |  |  | Transmital Date:MAY-25th-2022
Document Title: MTO For PAGA System |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-TE-TR-1004 |  |  | Transmital Date:MAY-25th-2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-TE-MT-0004_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بازگشت به مدارك مطالعات مهندسي پايه – پيوست 18 پيمان في مابين - در خصوص بلاك دياگرام سيستم هاي Telephone & Paging & Radio كه به شماره مدرك 1560-BK-NCS-TL-DIA-0001-04 ارائه شده است، تعداد اقلام مخابراتي در زيرسيستم هاي مورد اشاره در ترانسميتال TR-1004 با حداقل هاي بيان شده در مدرك مهندسي پايه متناسب نيست. علي ايحال باتوجه به تاييد مدرك BK-GCS-PEDCO-120-TE-BD-0005_D03 (Block Diagram For PAGA) توسط ذينفع اصلي پروژه، تعداد اقلام مخابراتي در مدرك MTO For PAGA System متفاوت از تعداد اقلام تاييد شده در مدرك Block Diagram ميباشد. از اين رو ضروريست تا پيمانكار دلايل فني و كارشناسي خودر را در خصوص كاهش/افزايش تعداد اقلام مخابراتي مورد نياز ذينفع اصلي پروژه بيان يا مدرك وربوطه را اصلاح نمايد نمايد. |  | BK-SUR-ENG-TEL-01-04603 | Jun-08th-2022 | مدرک بلوک دیاگرام شماتیک بیسیک بوده و بر اساس نیاز اصلی طرح و تعداد واقعی طراحی شده بلوک دیاگرام به روز رسانی میگردد
2 | لازم است تجهيزات Indoor نيز در برگه ايي جداگانه متصل به مدرك Block Diagram نمايش داده شوند. |  | BK-SUR-ENG-TEL-01-04603 | Jun-08th-2022 | تجهیزات یکپارجه بوده و امکان جداسازی تجهیزات indoor نمیباشد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: AP.Golrang | Signature |  |  |  | Clarified By: | Signature
| Date: 06-08th-2022 |  |  |  |  | Date: