## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-LI-0001_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0867 |  |  | Transmital Date: 27 Apr 2022
Document Title: Instrument Index |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-0867 |  |  | Transmital Date: 27 Apr 2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | فهرست مدارک مرجع تکمیل گردد. ( به عنوان مثال مدارک specification for instrumentation ، control/ESD/F&G System block Diagram configuration و .... اضافه گردد. |  | 01/2294/78910 | 1401/03/08 | مطابق خواست کارفرمای محترم اعمال گردید.
2 | قسمت ABBREVIATIONS تگمیل گردد. |  | 01/2294/78910 | 1401/03/08 | مطابق خواست کارفرمای محترم اعمال گردید.
3 | رنج های انتخابی برای تجهیزات می بایست براساس استاندارد با مدارک datasheet باشد |  | 01/2294/78910 | 1401/03/08 | مطابق خواست کارفرمای محترم اعمال گردید.
4 | در مورد استفاده از % برای واحد اندازه گیری سطح شفاف سازی گردد. |  | 01/2294/78910 | 1401/03/08 | مطابق خواست کارفرمای محترم حذف گردید.
5 | هرگونه تغییر در مدرک دیتاشیت و P&ID بایستی در این مدرک همسان سازی گردد. |  | 01/2294/78910 | 1401/03/08 | ملاحظه و بررسی گردید.
6 | تجهیزات تست و اندازه گیری بصورت جداگانه همراه با مشخصات ذکر گردند. |  | 01/2294/78910 | 1401/03/08 | از آنجائیکه پروژه حاضر در سایت موجود انجام می شود از WORKSHOP قدیم می توان استفاده کرد و ساخت و تجهیز WORKSHOP جدید در محدودهی کار این پروژه نمی گنجد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 10 May 2022 |  |  |  |  | Date: