## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W028-PEDCO-110-IN-PY-0001_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0958 |  |  | Transmital Date: 16 MAY 2022
Document Title: nstrument Location Layout Drawing - W028 |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-0958 |  |  | Transmital Date: 16 MAY 2022
[5 empty] | CRS No: PEDCO-CRS-BK-W028-PEDCO-110-IN-PY-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | sensing lines در نقشه نمايش داده شود. |  | BK-SUR-ENG-INS-01-04488 | 2022-05-29 | اضافه شد.
2 | با توجه به اينكه مدارك پيش نياز مانند P&ID و Plot Plan نهايي نشده است در صورت هر گونه تغييرات در مدارك مذكور در مدرك نيز اعمال گردد. |  | BK-SUR-ENG-INS-01-04488 | 2022-05-29 | ملاحظه شد.
3 | محل قرارگيري انواع تيوب ها در Tube Tray در قالب يك نوت مشخص شود. |  | BK-SUR-ENG-INS-01-04488 | 2022-05-29 | اضافه شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 30 May 2022 |  |  |  |  | Date: