## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-LD-0002_D00 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-1007 |  |  | Transmital Date: 25 May 2022
Document Title: ESD Logic Diagram - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1007 |  |  | Transmital Date: 25 May 2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-IN-LD-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اينكه مدارك پيش نياز مانند Process Cause and effect ارائه نشده است، اين مدرك قابل بررسي نمي باشد. |  | BK-SUR-ENG-INS-01-04627 | 2022-06-09 | مطابق خواست کارفرمای محترم، این مدرک عطف به مدارک پایه مانند P&ID و C&E به روز رسانی شد.
2
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 8 Jun 2022 |  |  |  |  | Date: