## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-TE-DW-0002_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0025 |  |  | Transmital Date:8/1/2021
Document Title: Telecom Typical Installation Details & Notes |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-TE-TR-0025 |  |  | Transmital Date: 8/1/2021
[5 empty] | CRS No: NISOC-CRS-BK-GNRAL-PEDCO-000-TE-DW-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | فاصله نصب سوکت RJ11 مشخص گردد |  | 1400-2294-194346 | 1400-06-21 | اضافه گردید . در نقشه های جانمایی نیز درج شده است.
2 | فاصله محل نصب تلفن بیرونی از کف زمین مشخص گردد |  | 1400-2294-194346 | 1400-06-21 | مشخص شده است . و با مثلث ویرایش مجدد مشخص گردید
3 | بخش استانداردهای کابل حذف گردد |  | 1400-2294-194346 | 1400-06-21 | نظر دریافتی مرتبط با مدرک نمی باشد
4 | بخش 7.4,7.8,7.9 استانداردهای کابل حذف گردد |  | 1400-2294-194346 | 1400-06-21 | نظر دریافتی مرتبط با مدرک نمی باشد
5 | در صورتی که مسیر عبور کابل مخابرات با موانعی از قبیل پل ،رودخانه و ...تداخل دارد لازم است نحوه اجرای ترانشه تهیه و ارایه شد |  | 1400-2294-194346 | 1400-06-21 | با توجه به شرح کار کابل کشی تلفن و پیجینگ و کابل حراستی فنس و داخل سایت چنین جزییات نصبی مورد نیاز نمی باشد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: AP.Golrang | Signature |  |  |  | Clarified By: | Signature
| Date: 08-08th-2021 |  |  |  |  | Date: