## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-TE-DW-0002-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0025 |  |  | Transmital Date: 8/1/2021
Document Title: Telecom Typical Installation Detail |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-TE-TR-0025 |  |  | Transmital Date: 8/1/2021
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-TE-DW-0002-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Flashing Beacon (light) for Outdoor telephone sets needed |  | BK-SUR-ENG-TEL-00-01300 | 08-10th-2021 | در ویرایش قبلی نیز وجود داشت . لطفا خواهشمند است رجوع شود به صفحات 4و8و19
2 | Fire telephone or hotline telephone set |  | BK-SUR-ENG-TEL-00-01300 | 08-10th-2021 | نحوه نصب تلفن و هاتلاین و فایر تلفن یکی می باشد و تیتر آن اضافه گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: AP.Golrang | Signature |  |  |  | Clarified By: | Signature
| Date: 08-08th-2021 |  |  |  |  | Date: