## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W007S-PEDCO-110-IN-PY-0003_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0967 |  |  | Transmital Date: 17 MAY 2022
Document Title: Instrument Location Layout - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-0967 |  |  | Transmital Date: 17 MAY 2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-IN-PY-0003_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | علائم اختصاری مربوط به ESDV برروی نقشه به صورت ESV یا ESDV نشان داده شود. |  | 01/2294/139962 | 1401/04/23 | اصلاح شد.
2 | سیگنال LEVEL موجود نمایش داده شود. ( در صورت فعال شدن LAHH میبایست ESDV ها بسته شوند.) |  | 01/2294/139962 | 1401/04/23 | LT مربوط به SUMP اضافه شد. این LT تنها به منظور مونیتورینگ تعبیه شده است. لازم به ذگر است مطابق توافقات HAZOP سیگنال LT تفکیک کننده موجود حذف شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 17 May 2022 |  |  |  |  | Date: