## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-CV-CN-0002 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-1294 |  |  | Transmital Date: 21-AUG-2022
Document Title:Calculation Note for offsite flood control system |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-T-1294 |  |  | Transmital Date: 21-AUG-2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-CV-CN-0002-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | برای چندمین مرتبه اعلام می گرددتمامی تغییرات انجام شده در مدارک نسبت به ترنسمیتال پیشین خود می بایست با REV.MARK مشخص گردند که در این مدرک رعایت نشده است. مقتضی است که دقت عمل بیشتری صورت پذیرد. |  | 1401-2294-205623 | 1401/6/9 | اعمال شد
2 | پاسخ ان پیمانکار به ردیف 5 از clarification by EPC contractor مورد تایید نمی باشد. با مراجعه به شرح پیمان -پیوست 18- شماره مدرک SDG-CV-GEM-1560-00-0005مربوط به Standard deatails surface drainage Ditch به کانال بتنی اشاره شده است. لذا اقدام گردد. |  | 1401-2294-205623 | 1401/6/9 | اصلاحات مقتضی لحاظ گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: