## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-CV-CN-0001 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-1324 |  |  | Transmital Date: 28-AUG-2022
Document Title: Calculation Note For Flood Control |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-T-1324 |  |  | Transmital Date: 28-AUG-2022
[5 empty] | CRS No: NISOC-CRS-BK-SSGRL-PEDCO-110-CV-CN-0001-D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بابت ایستگاه 260+1 چاه 28 بیشترین عرض رودخانه مطابق با نقشه های MODEL در حدود 7.5 متر است. لذا مشخصات ردیف 7 جدول مربوط به محاسبات کالورت های جاده دسترسی موقعیت یاد شده با لحاظ حریم استاندارد، می بایست تغییر یابد. پیشنهاد این امور احداث یک دستگاه پل می باشد. مقتضی است موضوع بررسی و اعلام گردد. |  | 1401-2294-216183 | 1401/6/17 | تعیین ابعاد کالورت ها بر حسب محاسبات هیدرولوژی و هیدرولیکی، انجام شده است و ظرفیت تعیین شده، متناسب با دبی هیدرولوژیکی مورد نیاز است. لذا در ایستگاه 1+260 به جهت یکپارچگی بیشتر در اجرا ،اقدامات مقتضی صورت گرفت و یک دستگاه پل در این کیلومتر پیش بینی گردید.
2 | باتوجه به اینکه نوع جریان، Uniform Flow در نظر گرفته شده است مقتضی است برای بررسی جداول درج شده در گزارش، محاسبات دستی تعیین مشخصات کالورت و ابعاد کانال های ذوزنقه ای (ستونFinal Dimention) تهیه و ارائه شود. |  | 1401-2294-216183 | 1401/6/17 | فایل های مورد نظر ضمیمه گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: