## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-TE-PY-0002_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1054 |  |  | Transmital Date: Jun-11th-2022
Document Title: Telecom Equipment Layout For Control Building |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-TE-TR-1054 |  |  | Transmital Date: Jun-11th-2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-TE-PY-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به تغییر نقشه اتاق کنترل ،مقتضی است پس از تایید و نهایی سازی مدرک معماری اتاق کنترل ،نسبت به ارسال مدرک برای بررسی این امور اقدام شود |  | 1401-2294-111532 | 1401-03-31 | مدرک بر اساس اخرین ویرایش معماری ساختمان مذکور ارسال شده است.
2 | تابلویIDF مربوط به تلفن در اتاق کنترل جانمایی و نمایش داده شود |  | 1401-2294-111532 | 1401-03-31 | در اتاق رک (AUXILARY ROOM ) جهت شمای بهتر در ساختمان و نزدیکی به ترنچ خروجی و توزیع بین سوکتها نشان داده شد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: AP.Golrang | Signature |  |  |  | Clarified By: | Signature
| Date: Jun-25th-2022 |  |  |  |  | Date: