## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-TE-PY-0002_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1054 |  |  | Transmital Date: Jun-11th-2022
Document Title: Telecom Equipment Layout For Control Building |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-TE-TR-1054 |  |  | Transmital Date: Jun-11th-2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-TE-PY-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | تعداد اقلام مخابراتي مربوط به بلند گوهاي سيستم PAGA متفاوت از تعداد آنها در مدرك BK-GCS-PEDCO-120-TE-BD-0004_D03 (Block Diagram For PABX) كه توسط توسط ذينفع اصلي پروژه تاييد شده ميباشد، طبقه همكف فاقد سيستم اعلان و هشدار ميباشد. تجهيز Revolving Light موجود ساختمان ابزاردقيق (اشاره شده در بلاك دياگرام) در مدرك مذكور جانمايي نشده است. |  | BK-SUR-ENG-TEL-01-04881 | Jun-25th-2022 | مدرک بلوک دیاگرام صرفا شماتیک می باشد و نقشه جانمایی تعداد اقلام را مشخص مینماید لذا نقشه دیاگرام در نسخه نهایی بر اساس تجهیزات واقعی چیدمان شده، به روز رسانی میگردد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: AP.Golrang | Signature |  |  |  | Clarified By: | Signature
| Date: Jun-25th-2022 |  |  |  |  | Date: