## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-MR-0004_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1112 |  |  | Transmital Date: 25 Jun 2022
Document Title: PMR For ON/OFF & Shutdown Valves - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1112 |  |  | Transmital Date: 25 Jun 2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-IN-MR-0004_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Min Requirement ها براي ITP در مدرك آورده شود. (Monitoring/Review/witness) |  | BK-SUR-ENG-INS-01-05249 | 1401/05/04 | ITP مطابق با فرمت پروژه می باشد
2 | Quality Control Plan (QCP) بر اساس مدارك پروژه مشخص شود. |  | BK-SUR-ENG-INS-01-05249 | 1401/05/04 | QCP مطابق با فرمت پروژه می باشد
3 | براي Trace راحت تر مدرك در يكي از ضمايم، مسئوليت هاي مربوط به Vendor و Purchaser مشخص شود. |  | BK-SUR-ENG-INS-01-05249 | 1401/05/04 | عبارات vendor و purchaser مطابق با DEFINITION تعریف شد.
4 | موارد مربوط به Actuator و Accessories در مدرك اضافه گردد. |  | BK-SUR-ENG-INS-01-05249 | 1401/05/04 | در part2 این مدرک بصورت نت اشاره شده است.
5 | Attachment-2 بر اساس نياز On/Off Valve بروز رساني گردد. |  | BK-SUR-ENG-INS-01-05249 | 1401/05/04 | اعمال گردید.
6 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي مي باشد. |  | BK-SUR-ENG-INS-01-05249 | 1401/05/04 | ملاحظه شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 26 Jul 2022 |  |  |  |  | Date: