## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W046S-PEDCO-110-CV-PY-0002 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-1185 |  |  | Transmital Date: 24.JUL.2022
Document Title: Civil and Structural drawings -W046S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-T-1185 |  |  | Transmital Date: 24.JUL.2022
[5 empty] | CRS No: PEDCO-CRS-BK-W046S-PEDCO-110-CV-PY-0002_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1401-2294-164809 | 1401/05/11 | اعمال گردید.
2 |  |  | 1401-2294-164809 | 1401/05/11 | در ویرایش چهارم مدرک BK-SSGRL-PEDCO-110-CV-CN-0001 با توجه به آخرین مذاکرات، کانال کنترل سیلاب طراحی و ارائه گردیده است. صفحه 16 مدرک حاضر نیز با توجه به مفاد گزارش مذکور اصلاح گردید.
3 |  |  | 1401-2294-164809 | 1401/05/11 | اعمال گردید. فایل به پیوست ارسال می‌گردد.
4 |  |  | 1401-2294-164809 | 1401/05/11 | اعمال گردید.
5 |  |  | 1401-2294-164809 | 1401/05/11 | اعمال گردید.
6 |  |  | 1401-2294-164809 | 1401/05/11 | در مقاطع متمایز است
7 |  |  | 1401-2294-164809 | 1401/05/11 | اصلاح گردید
8 |  |  | 1401-2294-164809 | 1401/05/11 | در محل اتصال دیوارهای بتنی به کف بتنی واتراستاپ پیش بینی شده است
9 |  |  | 1401-2294-164809 | 1401/05/11 | اصلاح گردید
10 |  |  | 1401-2294-164809 | 1401/05/11 | ماهیچه (ملاتی) نمایش داده شد
11 |  |  | 1401-2294-164809 | 1401/05/11 | اعمال گردید.
12 |  |  | 1401-2294-164809 | 1401/05/11 | اصلاح گردید
13
14
15
16
17
18
19
20
21
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: