## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-HV-DG-0004-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1058 |  |  | Transmital Date: 11/June/2022
Document Title: HVAC Flow Diagram For Extension of Existing Elect. Building |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-HV-TR-1058 |  |  | Transmital Date: 11/June/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-HV-DG-0004-D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اینکه در اسناد پیمان قید گردیده که برای ساختمان مذکور پکیج یونیت در نظر گرفته شود و محاسبات ظرفیت تجهیزات برای کل ساختمان در نظر گرفته شود این مدرک پس از تصمیم نهایی درخصوص انتخاب تجهیزات سرمایشی مورد بررسی قرار میگیرد. |  | 01/2294/109179 | 1401/03/30 | محاسبات ظرفیت برای کل ساختمان و با لحاظ کردن کامنتهای دریافت شده ،انجام شد. لطفا به Revision 01 محاسبات ارجاع شود. وتجهیزات با توجه به ظرفیت سیستم موجود (بر اساس مشخصات سازنده پکیج)، برای مابقی بارها اسپلیت یونیتهای دیواری و کانالی در نظر گرفته شده است
2
3
4
5
6
7
8
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: H.ADINEH | Signature
| Date: 06/29/2022 |  |  |  |  | Date: 09/21/2022