## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W046S-PEDCO-110-HV-CN-0001-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0731 |  |  | Transmital Date:14/MAR/2022
Document Title:HVAC Calculation Note For Switchgear Building - W046S |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-HV-TR-0731 |  |  | Transmital Date: 14/MAR/2022
[5 empty] | CRS No: NISOC-CRS-BK-W046S-PEDCO-110-HV-CN-0001-D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بازگشت به نامه شماره BK-PEDCO-NISOC-0012-ME-LT-28367-مورخ 1400/12/24 به اطلاع می رساند با توجه به موارد مطروحه در نامه 00/2294/443270 و از آنجا که نقشه های معماری مربوطه نهایی نشده و جانمایی کولر و فن نیز مشخص نمی باشد لذا امکان بررسی و اظهار نظر در خصوص این ترانسمیتال میسر نیست. |  | 01/2294/1285 | 1401/01/06 | محاسبات و نقشه های مربوطه با توجه به آخرین بازنگری نقشه های معماری انجام گرفته است و جانمایی اسپلیت یونیت ها و فنهای موردنیاز در نقشه HVAC SYSTEM LAYOUT مشخص می باشد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.naserizadeh |  |  | Clarified By: H.ADINEH | Signature
| Date: 5/7/2022 |  |  |  |  | 24/09 /2022