## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-HV-DG-0004-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1058 |  |  | Transmital Date:11/June/2022
Document Title: HVAC Flow Diagram For Extension of Existing Elect. Building |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-HV-TR-1058 |  |  | Transmital Date: 11/June/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-HV-DG-0004-D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Tag SUI -03C shall correct to 04 |  | BK-SUR-ENG-HVC-01-04922 | 2022-06-29 | IT HAS DONE.
2 | room pressure & temperature set point shall mention |  | BK-SUR-ENG-HVC-01-04922 | 2022-06-29 | IT HAS DONE.
3
4
5
6
7
8
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 06/29/2022 |  |  |  |  | Date: 09/21/2022