## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-TE-LI-0004_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1045 |  |  | Transmital Date: Jun-07th-2022
Document Title: Cable Schedule For PAGA System |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-TE-TR-1045 |  |  | Transmital Date: Jun-07th-2022
[5 empty] | CRS No: PEDCO-CRS-K-GCS-PEDCO-120-TE-LI-0004_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به نقطه نظرات ارائه شده در نامه شماره 96473 مورخ 21-03-1401 ذينفع اصلي پروژه همچنين نقطه نظرات كارشناسي شركت پتروايران ارائه شده به شماره پيگيري BK-SUR-ENG-TEL-01-04859 درخصوص پاسخ به ترانسميتال TR-0954، متراژ كابل هاي مورد استفاده زيرسيستم مخابراتي مذكور دستخوش تغيير خواهد گرديد. لذا جهت رعايت پيش نيازي، مدرك Cable Schedule For PAGA System ميبايست پس از نهايي سازي مدرك PAGA Equipment Layout For Area ارائه گردد. |  | BK-SUR-ENG-TEL-01-04876 | Jun-25th-2022 | لیست کابل بر اساس آخرین جانمایی مد نظر کارفرمای اصلی طرح ارایه گردیده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: AP.Golrang | Signature |  |  |  | Clarified By: | Signature
| Date: Jun-25th-2022 |  |  |  |  | Date: