## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-ME-SP-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1187 |  |  | Transmital Date: 24/July/2022
Document Title: Specification For Atmospheric Above Ground Welded Steel Tanks |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0105-ME-TR-01187 |  |  | Transmital Date: 24/July/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-ME-SP-0002-D01 |  |  | CRS Status: | C4
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اينكه محتواي اين مدرك در ارتباط كامل با استاندارد IPS-G-ME-100 بوده و مبناي عمل استاندارد IPS مي باشد لذا مي بايست مدرك بر اساس استاندارد مذكور تدوين گردد و همچنين از آخرين تغييرات ويرايش جديد استاندارد مبنا (API650) در اين مدرك بهره گرفت از اين رو مدرك نياز به بازنگري كلي دارد. |  | BK-SUR-ENG-MEC-01-05754 | 2022-09-24 | پیرو مذاکرات تلفنی و توافق با کارشناس محترم کارفرما(NISOC)، نقطه نظر ذکر شده در بخش SCOPE اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.Naserizadeh |  |  | Clarified By: H.Ghadyani | Signature | M.Fakharian
| Date: 9/24/2022 |  |  |  |  | Date: