## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-LI-0004 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0931 |  |  | Transmital Date: 11 May 2022
Document Title: I/O List For F&G Systems |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0105-ME-TR-0931 |  |  | Transmital Date: 11 May 2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0004_D01 |  |  | CRS Status: | C3
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | جوابيه كامنت شماره 1 در مدرك پيشين قابل قبول نبوده و نوع ديتكتورها مشخص شود. |  |  | 2022-05-28 | نوع دتکتور به لحاظ Addressable/ Conventional بودن در مدرک مشخص گردید.
2 | با توجه به اينكه مدرك پيش نياز اين مدرك F&G Location Layout (براي ساختمان و براي فيلد) داراي كامنت اساسي مي باشد. هر گونه تغيير در مدرك اعمال گردد. |  |  | 2022-05-28 | مدرک مطابق آخرین اصلاحات مدرک F&G Location Layout اصلاح و بروز رسانی گردید.
3 | Title در نسخه PDF درست شود. |  |  | 2022-05-28 | اصلاح گردید.
4 | در صورت تغيير در هر مرحله مدرك مي بايست به روز رساني گردد. |  |  | 2022-05-28 | مدرک مطابق آخرین نسخه از مدارک مرجع اصلاح و بروز رسانی گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 28 May 2022 |  |  |  |  | Date: