## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W028-PEDCO-110-PI-TB-0003-D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1164 |  |  | Transmital Date:16-July-2022
Document Title: TBE For Flanges-W028 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0104-PI-TR-1164 |  |  | Transmital Date:16-July-2022
[5 empty] | CRS No: NISOC-CRS-BK-W018S-PEDCO-110-PI-TB-0003-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 01/2294/169863 | 1401/05/18 | احتراما اعلام میگردد مدرک مذکور در این مقطع زمانی نهایی گردیده است.
2 |  |  | 01/2294/169863 | 1401/05/18 | احتراما در ویرایش بعدی مدرک مدنظر قرار خواهد گرفت.
3 |  |  | 01/2294/169863 | 1401/05/18 | احتراما در ویرایش بعدی مدرک مدنظر قرار خواهد گرفت.
4 |  |  | 01/2294/169863 | 1401/05/18
5 |  |  | 01/2294/169863 | 1401/05/18 | شرکت غرب فلنج در ویرایش بعدی مدرک TBE در میان شرکتهای لیست شده در TBE نمی باشد.
6 |  |  | 01/2294/169863 | 1401/05/18 | احتراما در ویرایش بعدی مدرک مدنظر قرار خواهد گرفت.
7 |  |  | 01/2294/169863 | 1401/05/18 | احتراما در ویرایش بعدی مدرک مشخصات ایتمها بر اساس محاسبات ضخامت بروز رسانی گردیده است.
8 |  |  | 01/2294/169863 | 1401/05/18 | احتراما اعلام میگردد مدارک مذکور در این مقطع زمانی نهایی گردیده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: