## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W028-PEDCO-110-PI-TB-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1164 |  |  | Transmital Date:16-July-2022
Document Title: TBE For Flanges-W028 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0104-PI-TR-1164 |  |  | Transmital Date:16-July-2022
[5 empty] | CRS No: PEDCO-CRS-BK-W028-PEDCO-110-PI-TB-0003-D01 |  |  | CRS Status: | C4
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اينكه مدارك PMS پروژه و MTO for Flanges-W028S هنوز نهايي نشده است و پيش نيازها رعايت نگرديده است لذا مدرك در اين مقطع قابل بررسي نمي باشد. |  | BK-SUR-ENG-PIP-01-05204 | 2022-07-20 | احتراما به اطلاع می رساند مدارکی که بدان اشاره گردیده است در این مقطع زمانی نهایی گردیده است.
2 | جهت ارسال TBE در ويرايش بعدي به AVL بودن شركتها دقت شود |  | BK-SUR-ENG-PIP-01-05204 | 2022-07-20 | احتراما در ویرایش های بعدی این مهم مدنظر قرار خواهد گرفت.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: J.Mousazadeh | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 17.July.2022 |  |  |  |  | Date : 17.July.2022