## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-EL-CN-0003-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1041 |  |  | Transmital Date: 06-Jun-2022
Document Title: Calculation Note For Cable Sizing |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-EL-TR-1041 |  |  | Transmital Date: 06-Jun-2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0003-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | صفحه 16 و 19 از 35، دمای محیط پیرو مکاتبات قبلی جهت طراحی الکتریکی 52 درجه درنظر گرفته شود. |  | 1401-2294-128509 | 1401-04-12 | اعمال گردید.
2 | در فایل اکسل Attachment 1 کاربرگ مربوط به کابل الکتروموتور 3.3 کیلوولت پمپ آب آتش نشانی ایجاد شود. |  | 1401-2294-128509 | 1401-04-12 | اعمال گردید.
3 | مسئولیت سایز و متراژ کابلها بر عهده آن پیمانکار است. |  | 1401-2294-128509 | 1401-04-12 | مسئولیت سایز و متراژ کابلها بر عهده پیمانکار است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 20-May-22 |  |  |  |  | Date: