## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-EL-CN-0003_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0879 |  |  | Transmital Date: 30-Apr-2022
Document Title: Calculation Note For Lighting System of Well Pads Security Building |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0102-EL-TR-0879 |  |  | Transmital Date: 30-Apr-2022
[5 empty] | CRS No: NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0003_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدرک plot plan به عنوان مرجع در نظر گرفته شود. |  | 1401-2294-82854 | 1401-03-09 | مطابق با آخرین ویرایش مدرک معماری اصلاح گردید.
2 | طبق فایل های پیوست ارسالی(plot plan)، برای بعضی اتاق ها نظیر wc نتایج روشنایی در فایل pdf ارائه نشده است و مقتضی است جهت کلیه فضاها نتایج روشنایی ارائه گردد همچنین بجاست جهت بهبود روشنایی، در فضای ورودی Resting room روشنایی منظور گردد. |  | 1401-2294-82854 | 1401-03-09 | با توجه به اینکه برای فضای توالت یک عدد چراغ سقفی در نظر گرفته شده است، از انجام مطالعات چشم پوشی گردید. لازم به ذکر است معماری ساختمان به طور کلی تغییر یافته است که به تبع آن محاسبات نیز به روز گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 10-May-22 |  |  |  |  | Date: