## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PR-CN-0007 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0862 |  |  | Transmital Date: 4/25/2022
Document Title: Calculation Note For Depressurizing (Min. Design Temperature ) |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0862 |  |  | Transmital Date: 4/25/2022
[5 empty] | CRS No:PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0007_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | تغييرات صورت گرفته بر محاسبات ابعاد ظروف در محاسبات اين مدرك نيز منعكس گردد. |  | BK-SUR-ENG-PCS-01-04334 | 2022-05-21 | اعمال گردید
2 | علت درنظر گرفتن 20 درصد مايع براي BDV-2132 چيست؟ در صورت عدم وجود مستندات لازم پيشنهاد مي گردد اين ميزان به صفر تقليل يابد. |  | BK-SUR-ENG-PCS-01-04334 | 2022-05-21 | اصلاح گردید
3 | قطر اورفيس براي BDV-2132 با شبيه سازي ارسالي مطابقت ندارد. اين مورد براي بقيه شير ها نيز مورد بازبيني قرار گيرد. |  | BK-SUR-ENG-PCS-01-04334 | 2022-05-21 | در مدرک فوق مساحت اورفیس گزارش شده است که با فایل شبیه سازی یکسان می باشد. در صورت وجود تناقض قطر حاصل از این محاسبات با مدرک RO سایزینگ ، قطرها در مدرک RO سایزینگ مجددا بازبینی خواهد شد.
4 | امكان اظهار نظر درخصوص BDV-2151 باتوجه به عدم دسترسي به ابعاد ظروف داخل پكيج نمزدا وجود ندارد همچنين پيشنهاد مي گردد حاشيه طراحي به جاي 20در صد فعلي (كه كمتر از مابقي شيرها مي باشد) به 50 درصد افزايش يابد. |  | BK-SUR-ENG-PCS-01-04334 | 2022-05-21 | اعمال گردید
5 | ميزان Back Pres. براي شير بسيار پايينتر از ميزان قيد شده در مدارك شبكه ارسالي مي باشد. و اين مهم سايز ارفيس را تحت تاثير قرار مي دهد. |  | BK-SUR-ENG-PCS-01-04334 | 2022-05-21 | اصلاح گردید
6 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-04334 | 2022-05-21 | اعمال گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021