## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-LI-0008 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0917 |  |  | Transmital Date: 09.May.2022
Document Title: Relief Load Summery |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0917 |  |  | Transmital Date: 09.May.2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0008_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | پيشنياز اين مدرك مدرك محاسبات شيرهاي ايمني مي باشد كه مدرك مذكور يكهفته بعد از ارسال اين مدرك دريافت شده است لذا ضروريست در ويرايش هاي آتي هر دو مدرك باهم و يا با فاصله زماني كم از يكديگر ارسال گردد. |  | BK-SUR-ENG-PCS-01-04505 | 31.May.2022 | اعمال میگردد.
2 | ضروريست تمامي نقطه نظرات ارائه شده بر مدرك محاسبات شيرهاي ايمني در اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-04505 | 31.May.2022 | اعمال گردید.
3 | كامنت پيشين: ضروريست محاسبات تخليه پكيج نمزدا پس از دريافت اطلاعات سازنده به مدرك اضافه گردد. |  | BK-SUR-ENG-PCS-01-04505 | 31.May.2022 | مورد تایید می‌باشد.
4 | كامنت پيشين: حالت Valve Fail. براي مخزن گاز سوخت در نظر گرفته شود. |  | BK-SUR-ENG-PCS-01-04505 | 31.May.2022 | باتوجه به نتایج جلسه HAZOP ، مقرر گردید PSV مخزن سوخت برای حالت FIRE سایز شود.
5 | نقطه نظرات ذينفع اصلي در خصوص مدرك مذكور اعمال گردد. |  | BK-SUR-ENG-PCS-01-04505 | 31.May.2022 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021