## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-RT-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1101 |  |  | Transmital Date: 6/21/2022
Document Title: Flare Radiation & Dispersion Study Report |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1101 |  |  | Transmital Date: 6/21/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-RT-0002_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نتايج حاصل از جلسه هاي HAZOP, HAZID, SIL در اين دياگرام اعمال گردد. |  | BK-SUR-ENG-PCS-01-05191 | 2022-07-19 | اعمال گردید
2 | جمله اشاره شده در آيتم 4.1 در خصوص فشار هاي عملياتي نياز به اصلاح دارد چرا كه مواردي از تخليه به فلر در فشار هاي نزديك اتمسفريك نيز وجود دارد . همچون برج Regeneration |  | BK-SUR-ENG-PCS-01-05191 | 2022-07-19 | اصلاح گردید
3 | اعداد نوشته شده براي سناريوي طراحي مطابقتي با مدرك Flare network Study report ندارد. |  | BK-SUR-ENG-PCS-01-05191 | 2022-07-19 | اصلاح گردید
4 | اطلاعات محيطي بويژه رطوبت در محاسبات اصلاح گردد. |  | BK-SUR-ENG-PCS-01-05191 | 2022-07-19 | اعمال گردید. لازم به ذکر است حداقل میزان رطوبت در مدارک پروژه 0% می باشد ولی با توجه به اینکه نرم افزار Flaresime حداقل میزان رطوبت کمتر از 4% را نمی پذیرد لذا میزان رطوبت 4% در نظر گرفته شده است.
5 | نهايي سازي اين مدرك منوط به نهايي شدن مدارك پيش نياز همچون محاسبات شبكه فلر مي باشد. |  | BK-SUR-ENG-PCS-01-05191 | 2022-07-19 | مورد تایید است
6 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-05191 | 2022-07-19 | اعمال گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021