## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W018S-PEDCO-110-PI-TB-0005-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0580 |  |  | Transmital Date:13-Feb-2022
Document Title: TBE For Gaskets-W018S |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0011-ME-TR-0580 |  |  | Transmital Date:13-Feb-2022
[5 empty] | CRS No:CRS-BK-W018S-PEDCO-110-PI-TB-0005-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مشخصات فنی ذکر شده اقلام لوله کشی خطوط سرچاهی، لیست شده در نامه فوق میبایست بر اساس PMS نهایی شده پروژه سفارش گذاری و تهیه گردد. |  | 00/2294/430726 | 1400/12/10 | احتراما این موضوع لحاظ گردیده است.
1 | از انجا که مشخصات فنی PMS خطوط لوله کشی سرچاهی (منضم به ترانسمیتال TR-0278) تا کنون نهایی نشده است لذا امکان بررسی و اظهار نظر در خصوص مشخصات فنی کالا وجود ندارد. |  | 00/2294/430726 | 1400/12/10 | بیشتر موارد موجود در مدارک PMS بررسی و حل و فصل گردیده و موارد باقیمانده مربوط به این مدرک نمیباشند.
2 | کلاس خطوط مندرج در ویرایش دوم PID خطوط لوله کشی سرچاهی ( منضم به ترانسمیتال TR-0345 ) با مدرک PMS انطباق ندارد و لذا امکان اظهار نظر در خصوص پیشنهاد فنی های ارسالی وجود ندارد. |  | 00/2294/430726 | 1400/12/10 | کلاس خطوط سرچاهی در مدرک (BK-SSGRL-PEDCO-110-PI-SP-0001) با PID همخوانی دارند.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: