## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W018S-PEDCO-110-PI-TB-0005-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0580 |  |  | Transmital Date:13-Feb-2022
Document Title: TBE For Gaskets-W018S |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0011-PI-TR-0580 |  |  | Transmital Date:13-Feb-2022
[5 empty] | CRS No:CRS-BK-W018S-PEDCO-110-PI-TB-0005-D00 |  |  | CRS Status: | C4
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اينكه مدارك P&ID و PMS پروژه هنوز نهايي نشده است و پيش نيازها رعايت نگرديده است لذا مدرك در اين مقطع قابل بررسي نمي باشد. |  | BK-SUR-ENG-PIP-00-03334 | 05.03.2022 | احتراما به اطلاع می رساند مدارکی که بدان اشاره گردیده است در این مقطع زمانی نهایی گردیده اند.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: J.Mousazadeh | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 23.Feb.2022 |  |  |  |  | Date : 23.Feb.2022