## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-PR-DT-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0808 |  |  | Transmital Date: 04/12/2022
Document Title: Process Data Sheets For Instrument Devices - W007S & Extension Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0808 |  |  | Transmital Date:04/12/2022
[5 empty] | CRS No: NISOC-CRS-BK-W007S-PEDCO-110-PR-DT-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | عطف به نامه شماره 1401/2294/43153 مورخ 1401/02/08 این امور در خصوص مدرک (P&ID-Extension of B/C Manifold) لازم است تغییر فشار کاری خط لوله ورودی به چندراهه، از فلنج بعد از شیر قطع اضطراری (ESDV) در نظر گرفته شود. لذا می بایست فشار طراحی شیر ESDV متناسب با کلاس مربوطه در نظر گرفته شود و در مدرک اعمال گردد. |  | 1401-2294-52764 | 1401/02/18 | اعمال گردید.
2 | مطابق بند فوق ، لازم است فشار طراحی مربوط به PG-1701/1702 و TRV-1701 مربوط به تمامی خطوط جریانی نیز متناسب با کلاس مزبور در نظر گرفته شده و در مدرک فوق اعمال گردد. |  | 1401-2294-52764 | 1401/02/18 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021