## HSE
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No. : BK-GNRAL-PEDCO-000-SA-DT-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0111 |  |  |  | Transmital Date: -09/21/2021
Document Title: MATERIAL SAFETY DATA SHEET |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-SA-TR-0111 |  |  |  | Transmital Date: -09/21/2021
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-SA-DT-0001 |  |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Brief Action | Client Conclusion
1 | عطف به ارسال دستورالعمل MSDS،از اين پس ترتيبي اتخاذ گردد تا دستورالعملهاي بخش HSE بر اساس اولويتهاي كاري و نيازمنديهاي پروژه كه با هماهنگي واحد HSE ستادي آن پيمانكار اولويت بندي ميشود ارسال گردد.در حال حاضر اولويت ارسال مدارك در بخش HSE به شرح ذيل مي باشد : 1- HSE PLAN 2- HI/RA 3- ERP 4- PTW 5- EMP |  | BK-SUR-HSE-HSE-00-01662 | 2021-03-10 | مطابق با توافق صورت پذیرفته با بخش HSE آن کارفرمای محترم ، مدرک مورد نظر براساس رویه های توافق شده مهندسی برای محاسبات مربوطه بخش ایمنی و فرآیند تهیه گردیده و صرفا داده های فنی آن مورد استفاده قرار می گیرد.
2 | ليست MSDS بر اساس خروجي شناسايي خطرات تكميل گردد (قبل از تهيه ليست مواد شيميايي شناسايي خطرات انجام پذيرد) |  | BK-SUR-HSE-HSE-00-01662 | 2021-03-10
3 | از سال 2012 بجاي MSDS از SDS استفاده مي گردد لذا نام دستورالعمل به SDS تغيير يابد (يك SDS مي تواند شامل MSDS هم باشد ولي برعكس آن صادق نيست) |  | BK-SUR-HSE-HSE-00-01662 | 2021-03-10
4 | در صفحه آخر مدرك قسمت " See attached files" مدركي پيوست نگرديده است و مدرك ناقص است. |  | BK-SUR-HSE-HSE-00-01662 | 2021-03-10
5 | گردش كار مدرك و مسئوليتها تشريح گردد. |  | BK-SUR-HSE-HSE-00-01662 | 2021-03-10
6 | بر اساس دستورالعمل هماهنگي پروژه مدارك ارسالي (در بخش HSE) به زبان فارسي ارسال گردد (لزوم ارسال برخي از مدارك از طرف پيمانكار به زبان انگليسي از قبل هماهنگ مي گردد) |  | BK-SUR-HSE-HSE-00-01662 | 2021-03-10
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: A.R.Joodaki | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date:3/10/2021 |  |  |  |  | Date: