## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-ME-DT-0001_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1336 |  |  | Transmital Date: 29/Aug/2022
Document Title: Mechanical Data Sheets For Oil Sump Pump (P-1701) |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0106-ME-TR-1336 |  |  | Transmital Date: 29/Aug/2022
[5 empty] | CRS No: NISOC-CRS-BK-W007S-PEDCO-110-ME-DT-0001_D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | همانگونه که پیش تر بارها متذکر شده است، ضروریست دلایل تغییر اطلاعات فرآیندی، فشار طراحی، فشار خروجی و... نسبت به ویرایش قبل در قالب Reply Sheet برای این امور بیان گردد. |  | 01/2294/229741 | 1401/06/28 | به اطلاع کارفرمای محترم می رساند تغییر اطلاعات فرایندی و فشار و مشخصات پمپ بر اساس محاسبات ارائه شده در بخش فرایند و برگه دیتا شیت فرایندی گزارش گردیده است.
2 | نوع پمپ معرفی شده نسبت به ویرایش قبل و همچنین اسناد پیمان تفاوت دارد. |  | 01/2294/229741 | 1401/06/28 | همانگونه که در پاسخ برگ قبلی ذکر شد، پمپ مذکور وظیفه تخلیه مایعات و آلودگی های جمع شده به علت تعمیر و تخلیه تجهیزات را دارد. مطابق با مدارک پایه و اسناد مناقصه ، این پمپ از نوع افقی بود ولی برای رفع مشکل NPSHاحتمالی در صورت گرفتگی foot valve ، این پیمانکار پیشنهاد تغییر نوع آن به پمپ عمودی VS4 را داد تا احتمال وقوع کاویتاسیون بواسطه نبود NPSH مورد نیاز برای پمپ های افقی کاهش یابد. با توجه به هد و دبی موجود و همچنین استعلام از سازندگان، پمپ عمودی از نوع VS1 پیشنهاد می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: H. Adineh | Signature | M. Fakharian
| Date: |  |  |  |  | Date: 10/08/2022