## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-ME-DT-0001_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1336 |  |  | Transmital Date: 29/8/2022
Document Title: Data Sheets For Oil Sump Pump - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0107-ME-TR-1336 |  |  | Transmital Date: 29/8/2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-ME-DT-0001_D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion | Clarification (By EPC Contractor)
| is it based on basic document? |  | BK-SUR-ENG-MEC-01-05770 | 2022-09-26 | Hirgan Reply: According to the client comment (NISOC) in Rev.00, this document has been issued based on ISO 5199 standard. please refer to attached file. |  |  | Noted & closed
| how did you reach to 20 barg for VS4's MAWP? please clarify. |  | BK-SUR-ENG-MEC-01-05770 | 2022-09-26 | Hirgan Reply: This item has been corrected. according to design pressure, MAWP shall not be less than 14.1 barg and shall be specified by vendor. |  |  | According to ISO 5199, the pump shall have MAPP 16 barg and hydrotest 24 barg, please revise it | MAWP shall be specified by vendor that with together hydrotest pressure will be checked at vendor's offer stage by purchaser (HIRGAN). also MAWP 16 barg at 20 degC is related to end suction pump type, whereas type of project's pump is VS1. however, it has been mentioned as note that vendor shall follow ISO 5199 standard for MAWP and hydrotest pressure.
| Sump depth sump diameter LLL to be specified |  | BK-SUR-ENG-MEC-01-05770 | 2022-09-26 | Hirgan Reply: Sump depth: 3m LLL: 0.1 m |  |  | Noted
1 | Please find the attached file |  | BK-SUR-ENG-MEC-01-05770 | 2022-09-26 | Please refer to attached pdf file for Hirgan reply
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.naserizadeh |  |  | Clarified By: H. Adineh | Signature | M. Fakharian
| Date:9/26/2022 |  |  |  |  | Date: 10/08/2022