## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0032 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0848 |  |  | Transmital Date: 4/20/2022
Document Title: Process Data Sheets For Instrument Devices |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0848 |  |  | Transmital Date: 4/20/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0032_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | فشار عملیاتی تجهیزات ابزار دقیقی نصب شده در خروجی پمپ P-2101 مربوط به SLUG CATCHER SYSTEM منطبق بر آخرین PFD و محاسبات هیدرولیک دریافتی مربوط به خط ارسال میعانات ایستگاه به کلاستر بینک نمی باشد . لذا می بایست فشار عملیاتی و متعاقب آن فشار طراحی تجهیزات مذکور اصلاح گردد. |  | 1401-2294-70086 | 1401/02/31 | فشار عملیاتی و طراحی خروجی پمپ P-2101 A,B طبق آخرین محاسبات هایدرولیک پمپ گزارش شده است و در SCOPE ایستگاه می باشد . اطلاعات کلاستر در خود مدرک کلاستر گزارش می شود .
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: