## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-PR-DT-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0807 |  |  | Transmital Date: 4/12/2022
Document Title: Process Data Sheets For Instrument Devices |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0807 |  |  | Transmital Date: 4/12/2022
[5 empty] | CRS No: NISOC-CRS-BK-PPL-PEDCO-320-PR-DT-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | فشار و دمای عملیاتی توپک ران بر اساس آخرین مدرک PFD و توپک گیر بر اساس نامه شماره 1400/2294/416040(1400/12/01) ارسالی این امور مورد بازنگری قرار گیرد . |  | 1401-2294-52773 | 1401/02/24 | به استحضار می رساند همانطور که در پاسخ نامه 1400/2294/416040(1400/12/01) اشاره شده است ، فشار طراحی خط لوله گاز به مقصد سیاه مکان بر اساس فشار طراحی کمپرسورهای ایستگاه جدید تقویت فشار بینک در نظر گرفته شده است.
2 | در خصوص سایر مدارک پیوست نظر خاصی مطرح نیست. |  | 1401-2294-52773 | 1401/02/24 | مورد تایید است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: