## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0032 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0848 |  |  | Transmital Date: 4/20/2022
Document Title: Process Data Sheets For Instrument Devices |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0848 |  |  | Transmital Date: 4/20/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0032_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق مذاكرات پيشين، اين امور نقطه نظرات خود را مستقيما بر داده برگ ابزار دقيق خواهد داد با اين وجود با توجه به پافشاري ذينفع اصلي بر تهيه اين مدرك، نقطه نظرات بصورت اجمالي بر اين مدرك نيز ارائه مي گردد. |  | BK-SUR-ENG-PCS-01-04314 | 2022-05-21 | مورد تایید می باشد .
2 | فشار عملياتي PG-2101 و تمامي ادوات بالادست شير كنترلي تصحيح گردد. |  | BK-SUR-ENG-PCS-01-04314 | 2022-05-21 | اصلاح گردید .
3 | فشار عملياتي و طراحي FG-2101 مورد بازنگري كلي قرار گيرد. |  | BK-SUR-ENG-PCS-01-04314 | 2022-05-21 | اصلاح گردید .
4 | فشار عملياتي PG-2103 و تمامي ادوات بالادست شير كنترلي تصحيح گردد. |  | BK-SUR-ENG-PCS-01-04314 | 2022-05-21 | اصلاح گردید .
5 | فشار عملياتي و طراحي FG-2102 مورد بازنگري كلي قرار گيرد. |  | BK-SUR-ENG-PCS-01-04314 | 2022-05-21 | اصلاح گردید .
6 | سيال PGو PT-2113 تصحيح گردد. |  | BK-SUR-ENG-PCS-01-04314 | 2022-05-21 | مطابق نتایج مهندسی ارزش ، تانک ذکر شده و DEGASSING DRUM حذف شده و ادوات ابزاردقیقی نیز حذف شده اند .
7 | سيال PVSV-2111 تصحيح گردد. |  | BK-SUR-ENG-PCS-01-04314 | 2022-05-21 | مطابق نتایج مهندسی ارزش ، تانک ذکر شده و DEGASSING DRUM حذف شده و ادوات ابزاردقیقی نیز حذف شده اند .
8 | فشار طراحي تمامي ادوات نصب شده بر تانك 2101 نادرست درج شده است. |  | BK-SUR-ENG-PCS-01-04314 | 2022-05-21 | مطابق نتایج مهندسی ارزش ، تانک ذکر شده و DEGASSING DRUM حذف شده و ادوات ابزاردقیقی نیز حذف شده اند .
9 | فشار طراحي و عملياتي تمامي ادوات نصب شده بر پمپ 2101 نادرست درج شده است. |  | BK-SUR-ENG-PCS-01-04314 | 2022-05-21 | اصلاح گردید .
10 | علت در نظر گرفتن فشار عملياتي ATM براي روتامترهاي تزريق مواد شيميايي چيست؟ |  | BK-SUR-ENG-PCS-01-04314 | 2022-05-21 | اصلاح گردید .
11 | باتوجه به اشكالات مورد اشاره فوق پيشنهاد مي گردد اطلاعات فرايندي در ويرايش بعد با دقت بالاتري تكميل گردد. |  | BK-SUR-ENG-PCS-01-04314 | 2022-05-21 | اصلاح گردید .
12 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-04314 | 2022-05-21 | اعمال گردید .
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: