## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-PR-DT-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0807 |  |  | Transmital Date: 4/12/2022
Document Title: Process Data Sheets For Instrument Devices |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0807 |  |  | Transmital Date: 4/12/2022
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-PR-DT-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | اطلاعات فرايندي PG-3210 نياز به بازنگري كلي دارد. |  | BK-SUR-ENG-PCS-01-03991 | 2022-04-19 | اصلاح گردید.
2 | فشار عملياتي تمامي تجهيزات با آخرين شبيه سازي مطابقت ندارد و نياز به بازنگري دارد. |  | BK-SUR-ENG-PCS-01-03991 | 2022-04-19 | مشخصات فرآیندی بر اساس آخرین شبیه سازی اصلاح گردید.
3 | نقطه نظر خاصی در خصوص این مدرک، مطرح نمی باشد. صرفا لازم است نقطه نظرات ذينفع اصلي اعمال گردد. |  | BK-SUR-ENG-PCS-01-03991 | 2022-04-19 | اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: