## Sheet 4
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-SA-DT-0004 |  |  |  |  | EPC Contractor Tr. No :BK-HD-PEDCO-T-0985 |  |  | Transmital Date: 2022/05/22
Document Title: Data Sheets For Deluge Valves |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-SA-TR-0985 |  |  | Transmital Date: 2022/05/22
[5 empty] | CRS No:NISOC-CRS- BK-GCS-PEDCO-120-SA-DT-0004-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | pressure سوییچ DPDT و Rating برابر با 24VDC/2A در نظرگرفته شود. |  | 01/2294/165031 | 1401/05/11 | اعمال گردید
2 | متعاقبا نظرات بخش مکانیک ارسال می گردد. |  | 01/2294/165031 | 1401/05/11 | ----------------
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: