## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PI-RT-0006-D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0677 |  |  | Transmital Date: 06-Mar-2022
Document Title: Wall Thickness Calculation Report |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-0677 |  |  | Transmital Date:06-Mar-2022
[5 empty] | CRS No: CRS-BK-GCS-PEDCO-120-PI-RT-0006-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | - بخش 6 مدرک حذف گردد. |  | 01/2294/27248 | 1401/01/28 | - اعمال گردید.
2 | - در صورتی که ضخامت بین دو SCH قرار گیرد، ضخامت SCH بالاتر در نظر گرفته شود و ضخامت نهایی می بایست از کمترین ضخامت بدست آمده بیشتر باشد. |  | 01/2294/27248 | 1401/01/28 | - ضخامتها بر همین اساس انتخاب شده اند.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date:13-Mar-2022 |  |  |  |  | Date:13-Mar-2022