## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PI-RT-0006-D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0677 |  |  | Transmital Date: 06-Mar-2022
Document Title: Wall Thickness Calculation Report |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-0677 |  |  | Transmital Date:06-Mar-2022
[5 empty] | CRS No: CRS-BK-GCS-PEDCO-120-PI-RT-0006-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در فايل اكسل محاسبات ، سرويس هاي ذكر شده در كلاسهاي مختلف دقيقاً مطابق جدول 1 در بخش 7.2 مدرك PMS مربوطه باشد. |  | BK-SUR-ENG-PIP-00-03538 | 2022-03-14 | - اعمال گردید.
2 | در كلاس هاي CN05 و CN07 و FN05 و FN07 درجه حرارت طراحي بر اساس دماي خروجي كمپرسور اصلاح گردد. |  | BK-SUR-ENG-PIP-00-03538 | 2022-03-14 | - اعمال گردید.
3 | در فايل محاسبات بخش Stress Relief در صورت عدم نياز حذف گردد. در صورت نياز PWHT در كلاسهاي مختلف بر اساس مدارك SPEC و WPS جوشكاري پروژه بررسي شده و اصلاحات لازم اعمال گردد. |  | BK-SUR-ENG-PIP-00-03538 | 2022-03-14 | - کلاسهایی که نیاز به Stress Relief ندارند بصورت (-) نشان داده شده و کلاسهایی که نیاز دارند PWHT نوشته شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date:13-Mar-2022 |  |  |  |  | Date:13-Mar-2022