## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK14-PEDCO-110-CV-PY-0001 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-1413 |  |  | Transmital Date: 19-SEP-2022
Document Title:General Civil Layout - BK14 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-T-1413 |  |  | Transmital Date: 19-SEP-2022
[5 empty] | CRS No: NISOC-CRS- BK-BK14-PEDCO-110-CV-PY-0001-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | جانمایی انجام شده برای Fire Fighting دارای ابهام است. مقتضی است دلایل تعیین این محل برای شفاف سازی اعلام گردد. |  | 1401-2294-238123 | 1401/7/4 | با توجه به خدمات مورد نیاز مندرج در شرح کار برای چاههای تعمیری Fire Fighting در نظر گرفته نشده است لذا حذف گردید.
2 | خط لوله - Oil Line- ترسیم نشده است |  | 1401-2294-238123 | 1401/7/4 | اعمال شد
3 | خط لوله - Burn Pit - ترسیم نشده است. |  | 1401-2294-238123 | 1401/7/4 | اعمال شد
4 | در نقشه مدل شیب بندی زمین درج شود. |  | 1401-2294-238123 | 1401/7/4 | اعمال شد
5 | محل استقرار گروه حفاری (اردوگاه) نمایش داده شود. |  | 1401-2294-238123 | 1401/7/4 | در نقشه با مختصات 4 گوشه M1 تا M4 مشخص شده است.
6 | استفاده از ترکیب تلرانس ارتفاعی در FGL یک اقدام ناقص است. مقتضی است یطور مشخص تعیین و درج شود. |  | 1401-2294-238123 | 1401/7/4 | اعمال شد. لازم به ذکر است که در نقشه های Rough Grading تراز دقیق کلیه نقاط به صورت شبکه ای درج گردیده است علاوه بر آن ترازها در مقاطع عرضی نقشه Rough Grading نشان داده شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: