## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-SP-0007_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0048 |  |  | Transmital Date: 14/AUG/2021
Document Title: Specification for Air Dryer Packages |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0006-ME-TR-0048 |  |  | Transmital Date: 14/AUG/2021
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0007_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | - |  | - | - | به اطلاع کارفرمای محترم می رساند نظر به مفاد پیوست 20 قرارداد، با توجه به عدم دریافت نقطه نظرات آن کارفرمای محترم ظرف مدت 15 روز (بیش از 400 روز) در مورد مدرک Specification for Air Dryer Package (ترنسمیتال T-0048)، مدرک مذکور تصویب شده تلقی گردیده و با وضعیت AFD ارسال خواهد گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: E. Sadeghi | Signature | M.Fakharian
| Date: |  |  |  |  | Date: 10/09/2022