## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-SP-0001_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0048 |  |  | Transmital Date: 14/AUG/2021
Document Title: Specification For Air Cooled Heat Exchangers |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0007-ME-TR-0048 |  |  | Transmital Date: 14/AUG/2021
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0001_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Refernece to EEMUA 143 to be added |  | BK-SUR-ENG-ROE-00-01467 | 2021-09-06 | This standard has already been mentioned in the specification but it has been modified to EEMUA 143.
2 | 5.5.f, List of spare parts shall include either full specification of the part or the supplier's part number (e.g. in reference drawings) |  | BK-SUR-ENG-ROE-00-01467 | 2021-09-06 | This sentence has been added to the caluse 5.5f.
3 | 7.1.1.1, tube-to-tubesheet joints shall also be able to sustain transportation / erection loads |  | BK-SUR-ENG-ROE-00-01467 | 2021-09-06 | This sentence has been added to the caluse 7.1.1.1.
4 | 7.1.10.1, project piping allowable nozzle and API 661, whichever is more strigent. |  | BK-SUR-ENG-ROE-00-01467 | 2021-09-06 | As there is no specification for allowable nozzle load, nozzle loading on a single header, shall not exceed three times the loads shown in Figure 6 and Table 4 in API Std. 661, 9th Edition (July 2015)
5 | 7.2.1.6, … site conditions |  | BK-SUR-ENG-ROE-00-01467 | 2021-09-06 | This phrase has been modified.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.BAVARSAD | Signature | H.naserizadeh |  |  | Clarified By: S.Salehi | Signature | M.Fakharian
| Date: 9/6/2021 |  |  |  |  | Date: 10/10/2022