## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-SP-0007_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0048 |  |  | Transmital Date: 14/AUG/2021
Document Title: Specification for Air Dryer Packages |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0006-ME-TR-0048 |  |  | Transmital Date: 14/AUG/2021
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0007_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Scope of supply: - Twin tower heatless regerative desiccant air dryer - Any necessary internals (Inlet & outlet diffusers, asdorptive media, …) - Exhaust silencers - Pre filteration & after filteration system (1+1) - Automatic draining (…) - Common Skid & support for all items within the package B.L. - Control Panel - Electrical Panel - Gauge Board - Dewpoint Transmitter -Diffrential Pressure Transmitter between the package inlet & outlet - Documentation & Drawings - All pipe-work (pipes, tubes, valves, ... )within the skid of the package - Wiring, cabling, junction boxes and glands within the base plate limits - Painting according to ... |  | BK-SUR-ENG-ROE-00-01467 | 2021-09-06 | All of these items already specified in the specification itself. No action is needed
2 | LIMITS OF SUPPLY: … Special tools & consumables for commissioning, start-up, calibration, & maintenance (if any) … |  | BK-SUR-ENG-ROE-00-01467 | 2021-09-06 | All of these items already specified in the specification itself. No action is needed
3 | Commissioning, installation supervision to be added to the scope of service |  | BK-SUR-ENG-ROE-00-01467 | 2021-09-06 | Noted
4 | 6.2.1: PSA air dryer is subject to the high cycle fatigue loads. FEA and ASME VIII-2 are necessary |  | BK-SUR-ENG-ROE-00-01467 | 2021-09-06 | Noted
5 | 6.2.1: in lieu of the "filter" use "filtration system". Inlet filteration system shall remove 99% of all liquid, particulates and oil particals carryover at operating flow range (with consideration of turn-down ratio) to the decsiccant towers |  | BK-SUR-ENG-ROE-00-01467 | 2021-09-06 | Already existed in Clause 6.2.1 of the specification.
6 | "The regeneration purge rate shall be automatically adjustable". Automatic adjustable purge rate is not feasible |  | BK-SUR-ENG-ROE-00-01467 | 2021-09-06 | Vendor will deviate if he can't follow this requirement and no more action is required
7 | "The regeneration purge rate shall be automatically adjustable". Automatic adjustable purge rate is not feasible please clarify. |  | BK-SUR-ENG-ROE-00-01467 | 2021-09-06 | Vendor will deviate if he can't follow this requirement and no more action is required
8 | "In the event of a power failure, the dryer shall continue to dry the incoming air to the specified dew point for a minimum of one hour." This time is not feasible for PSA dryers, please clarify. |  | BK-SUR-ENG-ROE-00-01467 | 2021-09-06 | Vendor will deviate if he can't follow this requirement and no more action is required
9 | The structural analysis for the structure and stress analysis for piping within the skid (NPS 6" and more) to be added |  | BK-SUR-ENG-ROE-00-01467 | 2021-09-06 | Noted
10 | N2 pressurized purging for shipping to be added |  | BK-SUR-ENG-ROE-00-01467 | 2021-09-06 | If it will be required based on the project Packing, Marking and Shippng specification, it shall be considered by vendor and no more action is required here.
11 | - |  | - | - | به اطلاع می رساند با توجه به عدم دریافت نقطه نظرات کارفرمای اصلی ظرف مدت 15 روز (بیش از 400 روز) بر روی مدرک Specification for Air Dryer Package (ترنسمیتال T-0048)، مطابق پیوست 20 قرارداد، مدرک مذکور تصویب شده تلقی می گردد و با وضعیت AFD ارسال خواهد گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.BAVARSAD | Signature | H.naserizadeh |  |  | Clarified By: E. Sadeghi | Signature | M.Fakharian
| Date: 9/6/2021 |  |  |  |  | Date: 10/09/2022